## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Jeet Bagdai | 2025-12-08 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2025-12-09 | Closed | Issue resolved and validated with sample programs
2 | Jeet Bagdai | 2025-12-09 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 2025-12-11 | Closed | Style detection accuracy improved
6 | Jeet Bagdai | 2025-12-21 | Variable naming inconsistencies were not flagged in some functions | Sprint 2 | Self | Standards | Enhanced naming convention checks in analysis module | 2025-12-22 | Closed | Consistency improved
7 | Jeet Bagdai | 2025-12-22 | Certain nested loops were not considered in complexity calculation | Sprint 2 | Self | Logical | Updated complexity calculation logic to include nested structures | 2025-12-23 | Closed | Complexity detection improved
8 | Jeet Bagdai | 2025-12-23 | Output formatting issues in displaying analysis results | Sprint 2 | Self | Functional | Refined UI rendering logic for better readability | 2025-12-24 | Closed | UI output improved
9 | Jeet Bagdai | 2025-12-24 | Error handling did not catch all syntax edge cases | Sprint 3 | Self | Logical | Improved parser validation and exception handling | 2025-12-25 | Closed | Edge cases handled
10 | Jeet Bagdai | 2025-12-25 | Delay in generating suggestions for larger code inputs | Sprint 3 | Self | Performance | Optimized request handling and processing pipeline | 2025-12-26 | Closed | Performance improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others